## Sheet1
STEP I (RFQ) Estimated Time Line |  |  | BOR Requirements
a. Owner issues public advertisement of RFQ | 2021-11-18 | -----
b. Deadline for written questions/requests for clarification (see Section 6). | 2021-11-24 | 4:00pm | issue addenda response at least 7 days prior to submission date (allow 3 days for responses)
c. Posting of Responses to Questions | 2021-12-01 | 4:00pm | 3 days
d. Deadline for submission of Statements of Qualifications | 2021-12-09 | 2:00pm | at least 21 days after posting date
e. Owner completes evaluation, post results, and issues notification to finalist firms | 2021-12-15 | ----- | recommended 7 day review period
f. Owner conducts Mandatory Pre-Proposal Site Visit for finalists | 2021-12-22 | TBD | at least one week after notification
g. Deadline for finalist submission of written questions and requests for clarification | 2021-12-31 | 14:00 | at least one week from site visit (allow 5 days for responses)
h. Posting of Responses to Questions | 2022-01-07 | 4:00pm | 5 days
i. Deadline for submission of Design Team Proposals | 2022-01-14 | 14:00 | at least one week from Q&A
j. Owner interviews finalist firms and Fee Proposals are due | 2022-01-21 | TBA | at least one week from receipt of proposals
INSTRUCTIONS FOR USE:
Please see attached. The trick is to use this as just a starting point. You change the first date to the posting date that you wish and all the dates adjust accordingly to the BOR prescribed/recommended dates. You have to manually review the calendar and check each sequential date to confirm that they fit you specific project needs and that dates don’t land on a weekend or on a Monday for Submittals.